# Center for Advanced Manufacturing NTU CAM

# STRATEGIC PLAN 2019- 2023

# Table of Contents

History3

Future Growth Opportunities4

Vision Statement 	6

Priorities, Goals, Objectives	7

Implementation Steps	16

# History

Navajo Technical University has been steadily increasing its capacity to provide quality science, technology, engineering, and mathematics (STEM) education to Native American students since it was founded in 1979. The University is a fully accredited institution of higher learning that offers certificate programs for job preparedness and associate, baccalaureate, and graduate degrees to a student body that primarily consists of Navajo tribal members, but also serves other populations, such as Pueblo and Ute students, in Northwest New Mexico and Eastern Arizona.  Students that attend NTU come from an Arizona Navajo economic landscape that features a high unemployment rate and a poverty rate near 42%. As a result, many of the people and the communities in which they reside are trapped in cycles of poverty that have limited their ability to access resources needed in order to sustain a healthy way of life.

In 2012, with partial funding from NSF and NASA, Navajo Technical University established a Fabrication Laboratory (Fab Lab) in the Center for Digital Technologies to support STEM education by providing the personnel and equipment for engineering projects, research, fabrication, software modeling services, and hardware and software training and support.  Industry demands that graduates from engineering programs know how to utilize new technologies within the engineering disciplines, along with theoretical mathematics-based courses. NTU’s Fab Lab provides a platform for project-based, hands-on STEM education. Students learn by designing and creating objects relevant to their course of study. Empowered by the experience of making something themselves, they both learn and mentor each other, improving understanding of basic principles and gaining knowledge about the technologies, machines, materials, design process, and engineering that goes into invention and innovation. Rather than relying on a fixed curriculum, learning happens in an authentic, engaging, personal context, one in which students go through a cycle of imagination, design, prototyping, reflection, and iteration as they find solutions to challenges or bring their ideas to life. Examples of Digital Manufacturing student projects include capturing the current state of the Navajo Nation Council Chambers for historical preservation and then working to upgrade the space for more efficient use, and assisting a company, Business Environments, with exploring ways to use data for better efficiency in their workflow.

Navajo Technical University’s institutional strategic plan includes priorities that leverage the commitment to economic development on the Navajo Nation. Advanced Manufacturing at NTU strives to stay in front of the industry by offering education, research and prototype service for the Navajo students, for the AM industry and for the partners and clients waiting for opportunities to enter more comprehensive solutions to AM needs. This initiative is being driven by revenue generation challenges on the Navajo Nation, due mainly to decline in coal markets which provide ~ 1/5 of NN budget. One of the top priorities of the Navajo Nation administration is to replace these revenues and job losses.

The fundamental vision of the of the Center for Advanced Manufacturing is to develop a Center of Excellence in advanced manufacturing technology and to provide the Navajo Nation and New Mexico the tools to be a leader in the industry as well as in research and development of Advanced Manufacturing. The four priorities of the plan are: Education Support, Research, Industry Partnerships, and Economic Development.

The Center for Advanced Manufacturing will develop a Navajo workforce, serving the needs of the Center, and also providing sustainable educational programs, research and technology transfer opportunities. Navajo students, both K-12 and college can move through the experiential learning from the Center, while beginning their own work experience both at NTU and with industry partners.

“One of the things NTU has long believed is that by developing strong relationships with private industry, we can create a model for combating generational poverty. This model will bring not only honor on those who partner with us, giving them unique marketing opportunities, but can also help demonstrate how good corporate citizenship can help improve society.

Today we both celebrate and roll up our sleeves to work at developing a new industry on the Navajo Nation, to enhance economic development, workforce expansion, and the opportunity for our Navajo students to become a part of the exploding industry of Advanced Manufacturing.

We offer our Advanced Manufacturing Lab to serve as the hub for education, research, training, apprenticeships, and internships, and look forward to helping coordinate facilities on the Navajo Nation such as testing, metrology, and high volume production.

President Elmer Guy

Welcome Address to Boeing Corporation

August 2018

# Future Growth Opportunities in Advanced Manufacturing

Technological advancements are transforming manufacturing not just in internal product production but also in both the supply chains and distribution channels. While the previous 10 to 15 years were defined by outsourcing and off shoring to find low cost alternatives for manufacturing, reduced labor costs, the rise of 3-D printing, and cheaper energy domestically have cut into the overhead costs of manufacturing and are promoting a renewed look at moving more manufacturing back to the states. Technologies such as 3-D printing allow a software-savvy employee to print a product onsite for a customer in real time, which is also leading manufacturing to become highly distributed and democratized. The result is that advanced manufacturing allows for the establishment of factories that leverage local talent, resulting in the democratization of manufacturing. Table 1 summarizes future growth opportunities by area.

Market growth in additive manufacturing ranges from $7 billion to $21.3 billion by 2020. The National Institute of Standards and Technology (NIST) estimates that 30% market saturation will be valued at $617.7 billion and achieved by 2065.

3D printing will potentially have a greater impact globally over the next 20 years than all of the innovations from the industrial revolution combined. Although traditional manufacturing will likely still hold a place in the competitive landscape in the years to come, the next 10 to 20 years promise to reveal a rapid increase in the innovations made possible by 3D printing. The private sector will want to continue working towards embracing this technology as a platform to create new businesses, business models, products and services. The market for rapid prototyping is forecast to increase to $903 million by 2021.

The global metrology services market is anticipated to reach $824.6 million by 2020, according to a new study by Grand View Research, Inc. Increasing demand among end-users in different industries for precise components with low tolerance limits such as power generation, electronics, and automotive is anticipated to drive growth. Also, technological innovation in the field of metrology is expected to positively impact growth. These advancements further influence growth pattern and stimulate new product and software developments for industry players. Consequently, demand for advanced measurement tools and services are expected to aid manufacturers in competently tapping data such as 3-D modeling and measurements.

Non-destructive inspection technologies revenue is expected to increase to $11.39 billion by 2022. The forecast period offers huge growth potential for technologies such as computed tomography, phased array ultrasonic testing, and data management tools, as these techniques are more efficient in terms of deriving accurate results.

| Table 1: Future Growth Opportunities in Advanced Manufacturing |  |
| --- | --- |
| Area: | Market projection: |
| Additive manufacturing | $7 billion to $21.3 billion by 2020, at a 20% CAGR |
| Rapid prototyping | $903 million by 2021, at a 26.8% CAGR from 2016 to 2021 |
| Metrology services market | $824.6 million by 2020 |
| Non-destructive inspection technologies | $11.39 billion by 2022, at a 8.3% CAGR from 2016 to 2022 |

# The Role of the Strategic Plan

The adoption and implementation of the Center for Advanced Manufacturing Strategic Plan represents Navajo Technical University’s commitment to embracing a proactive and comprehensive planning approach to move toward higher education offerings that create significant and lasting change by increasing access to education and employment for Navajo people. The plan will guide the creation of an additive manufacturing ecosystem – CAD (design and simulation), Machine operation (machine prep, parameter setting, part build, part removal, machine cleaning and maintenance), post-processing (part removal from plate, support material removal, heat treatment, machining, polishing, etc.), part validation (metrology, mechanical properties and characterization).

The Strategic Plan will be used as a framework for determining specific measurable goals. A designated work group will present bi-annual recommendations, with measurable outcomes, for each of the priority areas, to the President of the University as well as Advanced Manufacturing leaders.

2019-2023 Strategic Initiatives

The vision of the of the NTU Center for Advanced Manufacturing is to develop a Center of Excellence in advanced manufacturing technology and to provide the Navajo Nation and New Mexico the tools to be a leader in the Advanced Manufacturing industry in education, research, industry partners and economic sustainability.

The mission of the NTU Center for Advanced Manufacturing is to develop a Navajo workforce and to serve the needs of advanced manufacturing on the Navajo Nation and at NTU. The Center will provide sustainable educational programs, research and technology transfer opportunities. Navajo students, both K-12 and college, can benefit from experiential learning, in order to begin their own work experience both at NTU and with industry partners.

# Priority 1

Education Support: The NTUCAM will provide STEM programs the infrastructure to implement experiential learning, hands-on projects and practical application to classroom theory. The NTUCAM will provide internship opportunities for students in metrology, materials properties and characterization, additive manufacturing and machining.

# Goals and Objectives

- Equip the Center with equipment relevant to advanced manufacturing based curriculum

  - Support Metrology Education (New Building)

    - TEA grant to help equip lab

    - Other grants to support

    - Create educational Lab

  - Support Materials Education (New Building)

    - TEA grant to help equip lab

    - Other grants to support

  - Support Machining Education (Fabrication Lab)

    - TEA grant to help equip lab

    - Other grants to support

  - Support Additive Manufacturing (Fabrication Lab)

    - TEA grant to help equip lab

    - Other grants to support

    - Purchase Metal machine

- Create an institutional culture

  - Engage all faculty, staff and students

  - Create together culturally responsive education.

- Map NTU CAM curriculum

  - Adjust curriculum content to reach the goals of Navajo Nation (plant or small manufacturing design, material properties skills and knowledge, metrology skills and knowledge, pathway to research with academia)

  - Adjust curriculum content to reach the goals of NTU

# Priority 2

Research: To develop a comprehensive research agenda which arises from the projects and focus of the Center. Research will leverage and build upon the Center’s equipment and materials and previous research.

# Goals and Objectives

- Lab Personnel

  - Develop Organizational Chart to manage labs (developed)

- Additive Manufacturing Research

  - Research grants

  - Industry Mentor/student collaboration grant opportunities

    - NSF – Jody Chase

  - Senior students build research portfolios, working with industry mentor

- Research Activities

  - Students working in lab conducting research

- Research planning

  - Develop a comprehensive research strategic plan, which details resources needed, funding possibilities, industry mentors, and NTU priorities

  - Involved NN and other stakeholders in research plan

# Priority 3

Industry Partnerships: To create a national and international sphere of partners that support and are supported by the Advanced Manufacturing infrastructure at NTU and on the Navajo Nation

# Goals and Objectives

- Develop Industry Partnerships in Advanced Manufacturing

- Internships (industry based internships)

- Apprenticeships

- Workforce Development

Priority 4

Economic Sustainability: Develop and implement a revenue generation strategy that ensures the creation of a new economic structure on the Navajo Nation.

# Goals and Objectives

- Develop the LLC arm of NTU to enable revenue generation

  - Tony

- Build the infrastructure to engage in contracting for services and research

  - Certification

  - Training

- Create a plan for Services:

  - metrology/inspection services,

  - material testing and characterization services,

  - prototyping using 3D printing polymers and metals

  - Research revenue

  - Metal AM services

# APPENDIX A -

IMPLEMENTATION for NTU CAM

(We can create a chart here to record the steps, budget, leadership that enable each of the objectives)

# Priority 1 Education Support

# Goals and Objectives - Equip the Center with equipment relevant to advanced manufacturing based curriculum

|  | Leadership | Budget | Secured Funding | Unmet Need | Progress |
| --- | --- | --- | --- | --- | --- |
| Support Metrology Education |  |  |  |  |  |
| Establish Educational Lab | Scott | $2.5 million | EDA & NN $2.5million | $0.00 | Building A/E services and TEA funding for equipment |
| Equipment for lab | Scott | $300,000 | Portion of $3.5 million TEA | $275,000 | Most equipment already acquired – need granite tables |
| Establish NTU Budget | Scott, Casmir, Geraldine | $5,000year | $0.0 | $5,000/year | None |
| Create Metrology Program | Scott, TBD | $150,000 | Possible Perkins Funding | $150,000 | Equipment in place, need instructor. Curriculum developed (draft) |
| Support Material Science Education |  |  |  |  |  |
| Establish Lab | Scott | $5,000 | Portion of $3.5 million TEA | $0.0 | New Building being designed |
| Establish NTU Budget | Scott, Casmir, Geraldine | $5,000year | $0.0 | $5,000/year | None |
| Support Machining Education |  |  |  |  |  |
| Equipment for lab | Scott | $300,000 | Portion of $3.5 million TEA | $0.00 | EDM, Lathe, Horizontal Band Saw. |
| Establish NTU Budget | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Support Additive Manufacturing Education |  |  |  |  |  |
| Establish NTU Budget for Polymers | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Acquire Metal AM Printer | Scott | $2,000,000 | $0.0 | $2,000,000 | Grant submitted for $445,000 Optomec machine – EOS and Optomec Hybrid still unfunded |
| Create metal AM Training program | Scott, advisory group | $0.0 | NSF TEA grant | $0.0 | Working with Optomec for DED training, Have Joshua Toddy working at UNL for training |
| Develop AM tracking system | Scott, IT, Greg | $0.0 | $0.0 | $0.0 | Implemented ticketing tracking system |
| Create an institutional culture |  |  |  |  |  |
| Engage all faculty, staff and students |  |  |  |  |  |
| Create together culturally responsive education |  |  |  |  |  |
| Map NTU CAM curriculum |  |  |  |  |  |
| Adjust curriculum content to reach the goals of Navajo Nation (plant or small manufacturing design, material properties skills and knowledge, metrology skills and knowledge, pathway to research with academia) |  |  |  |  |  |
| Adjust curriculum content to reach the goals of NTU |  |  |  |  |  |

# Priority 2 Research

To develop a comprehensive research agenda which arises from the projects and focus of the Center. Research will leverage and build upon the Center’s equipment and materials and previous research.

# Goals and Objectives

|  | Leadership | Budget | Secured Funding | Unmet Need | Progress |
| --- | --- | --- | --- | --- | --- |
| Research Support - Metrology |  |  |  |  |  |
| Establish Metrology Lab to support research activities | Scott | $2.5 million | EDA & NN $2.5million | $0.00 | Building A/E services and TEA funding for equipment |
| Equipment for lab | Scott | $300,000 | Portion of $3.5 million TEA | $275,000 | Most equipment already acquired – need granite tables |
| Establish NTU Budget | Scott, Casmir, Geraldine | $5,000year | $0.0 | $5,000/year | None |
| Attain Lab Certification | Scott | ~$20,000/year | $0.0 | $20,0000 | Filing of Certification, budget for certifications of equipment/year |
| Research Support - Material Testing and Characterization |  |  |  |  |  |
| Establish Certification for Lab (ISO 17025 & NADCAP) | Scott | $Unknown | Portion of $3.5 million TEA | $0.0 | Certification documentation being filed. |
| Establish NTU Budget | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Research Support - Machining Support for Metal AM |  |  |  |  |  |
| Equipment for lab (covered by education) | Scott | $300,000 | Portion of $3.5 million TEA | $0.00 | EDM, Lathe, Horizontal Band Saw. |
| Establish NTU Budget | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Support Additive Manufacturing Education |  |  |  |  |  |
| Establish NTU Budget for Polymers | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Acquire Metal AM Printer | Scott | $2,000,000 | $0.0 | $2,000,000 | Grant submitted for $445,000 Optomec machine – EOS and Optomec Hybrid still unfunded |
| Create Training program | Scott, advisory group | $0.0 | NSF TEA grant | $0.0 | Working with Optomec for DED training, Have Joshua Toddy working at UNL for training |
| Research Planning |  |  |  |  |  |
| Engage all faculty, staff and students |  |  |  |  |  |
| Create Comprehensive Research Outline to leverage funding |  |  |  |  |  |
| Support personnel | Scott – other grant writers | $560,000/year | $260,000 | $300,000 | Grants for next 5 years to help offset costs |

# Priority 3 Industry Partnerships

# To create a national and international sphere of partners that support and are supported by the Advanced Manufacturing infrastructure at NTU and on the Navajo Nation

# Goals and Objectives

|  | Leadership | Budget | Secured Funding | Unmet Need | Progress |
| --- | --- | --- | --- | --- | --- |
| Develop Industry Partners |  |  |  |  |  |
| Metrology | Scott |  | 15,000/year | $ | V&M Global |
| Materials | Scott | $ |  | $ | UNL, University of Utah, Oklahoma |
| Metal AM | Scott | $ | $0.0 | $ | Optomec, sigma labs |
| Internships |  |  |  |  |  |
| Metrology | Scott | $Unknown | Portion of $3.5 million TEA | $0.0 | Certification documentation being filed. |
| Machining | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Metal AM |  |  |  |  |  |
| Agencies |  |  |  |  |  |
| Apprenticeships |  |  |  |  |  |
| Equipment for lab (covered by education) | Scott | $300,000 | Portion of $3.5 million TEA | $0.00 | EDM, Lathe, Horizontal Band Saw. |
| Establish NTU Budget | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Workforce Development |  |  |  |  |  |
| Establish NTU Budget for Polymers | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Acquire Metal AM Printer | Scott | $2,000,000 | $0.0 | $2,000,000 | Grant submitted for $445,000 Optomec machine – EOS and Optomec Hybrid still unfunded |
| Create Training program | Scott, advisory group | $0.0 | NSF TEA grant | $0.0 | Working with Optomec for DED training, Have Joshua Toddy working at UNL for training |

Priority 4 Economic Sustainability

Develop and implement a revenue generation strategy that ensures the creation of a new economic structure on the Navajo Nation.

# Goals and Objectives

|  | Leadership | Budget | Secured Funding | Unmet Need | Progress |
| --- | --- | --- | --- | --- | --- |
| Develop the LLC arm of NTU |  |  |  |  |  |
| Create Business | Tony, Sharon, Admin |  |  | $ | Not sure |
| Build the infrastructure to engage in contracting for services and research |  |  |  |  |  |
| Metrology | Scott | $Unknown | Portion of $3.5 million TEA | $0.0 | Certification documentation being filed. |
| Machining | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Metal AM |  |  |  |  |  |
| Agencies |  |  |  |  |  |
| Create a plan for Services |  |  |  |  |  |
| Expertise | Scott | $300,000 | Portion of $3.5 million TEA | $0.00 | EDM, Lathe, Horizontal Band Saw. |
| Workforce | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Management Plan |  |  |  |  |  |
| Workforce Development |  |  |  |  |  |
| Establish NTU Budget for Polymers | Scott, Casmir, Geraldine | $10,000year | $0.0 | $10,000/year | None |
| Acquire Metal AM Printer | Scott | $2,000,000 | $0.0 | $2,000,000 | Grant submitted for $445,000 Optomec machine – EOS and Optomec Hybrid still unfunded |
| Create Training program | Scott, advisory group | $0.0 | NSF TEA grant | $0.0 | Working with Optomec for DED training, Have Joshua Toddy working at UNL for training |

- Develop the LLC arm of NTU to enable revenue generation

  - Tony

- Build the infrastructure to engage in contracting for services and research

  - Certification

  - Training

- Create a plan for Services:

  - metrology/inspection services,

  - material testing and characterization services,

  - prototyping using 3D printing polymers and metals

  - Research revenue

  - Metal AM services

Action Items:

- Acquire a Metal 3D printer

  - Optomec DED machine – Hybrid (School, Navajo Nation, or private investor) $800,000

    - Grant written and submitted to purchase basic Optomec ($400k)

  - Powder Bed Laser Fusion machine

    - EOS (used by partners and Boeing)

    - Renishaw (good leasing options)

- Metrology and Materials Testing Building

  - Funded

    - RFP Design Services – Dec 2018

    - RFP Construction – March 2019

    - Completion - Fall 2019

    - Fully operational Dec 2019

    - Certifications 2021(?)

- Machinist Program

  - NTU Bond Wilson Instructional Site

    - Grant Written and submitted ($3 million)

    - Plan B – Salt River Project (SRP)

  - Key part of Additive Ecosystem

- Funding for Student/graduate Technicians

  - Funded by each research grant (percentage)

  - Grants written that includes Technicians

  - (Instructors suggested hiring someone with experience – told them why they don’t have confidence in our graduates, work with them to gain the experience)